Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 15 February 2026 |
| --- | --- |
| Team ID | LTVIP2026TMIDS24232 |
| Project Name | Gemini Historical Artifact Description |
| Maximum Marks | 5 Marks |

1. Product Backlog, Sprint Schedule, and Estimation

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Core Setup & UI | USN-1 | Set up Streamlit environment and configure Gemini API connection securely | 2 | High | Dev 1 |
| Sprint-1 |  | USN-2 | Create "Premium Museum" CSS theme with dark mode and serif fonts | 3 | High | Designer/Dev 1 |
| Sprint-1 | User Input Handling | USN-3 | Implement text input field for artifact names with validation | 2 | High | Dev 2 |
| Sprint-1 |  | USN-4 | Implement image uploader supporting JPG/PNG formats | 3 | High | Dev 2 |
| Sprint-1 | Output Display | USN-5 | Create "Glassmorphism" result cards for displaying AI output | 3 | Medium | Designer/Dev 1 |
| Sprint-2 | AI Logic | USN-6 | Develop prompt engineering logic for structured text descriptions | 3 | High | Dev 1 |
| Sprint-2 |  | USN-7 | Integrate Gemini Vision capabilities for image analysis | 5 | High | Dev 1 |
| Sprint-2 | Features | USN-8 | Add "Did You Know?" random facts sidebar widget | 2 | Low | Dev 2 |
| Sprint-2 |  | USN-9 | Implement file download functionality (TXT/MD) | 2 | Medium | Dev 2 |
| Sprint-2 |  | USN-10 | Add loading animations and status indicators | 2 | Low | Designer |

2. Project Tracker, Velocity & Burndown Chart

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 13 | 5 Days | 15 Jan 2026 | 20 Jan 2026 | 13 | 20 Jan 2026 |
| Sprint-2 | 14 | 5 Days | 21 Jan 2026 | 21 Jan 2026 | 14 | 26 Jan 2026 |
| Sprint-3 | 12 | 5 Days | 27 Jan 2026 | 27 Jan 2026 | 12 | 1 Feb2026 |
| Sprint-4 | 10 | 10Days | 2 Feb 2026 | 2 Feb 2026 | 10 | 12 Feb 2026 |

3. Velocity Calculation

Assumption:

- Sprint Duration: 10 Days

- Average Velocity of the Team: 13.5 Points per Sprint (Average of Sprints 1 & 2:

(13+14)/2)

Calculating Average Velocity (AV) per Iteration Unit (Story Points per Day):

- Formula:

Velocity (Points per Sprint) / Sprint Duration (Days)

- Calculation:

13.5 / 10 = 1.35

Result: The team's average velocity is 1.35 Story Points per Day.

4. Burndown Chart Data (Example for Sprint 1)

Imagine a line graph plotting these points:

- Day 1: 13 Points Remaining (Start)

- Day 3: 10 Points Remaining

- Day 5: 7 Points Remaining

- Day 8: 3 Points Remaining

- Day 10: 0 Points Remaining (Completion)

(A Burndown Chart visualizes this data, showing the "Actual Work Remaining" line potentially fluctuating around the "Ideal Work Remaining" diagonal line).